## Slide 1: ‘Agility is the TOOL, not the Master’ : Practical Agile Systems Engineering Tools including My Ten Key Agile Principles and several case studies
Tom Gilb
“
Build Stuff 13, 9.12.2013 Monday 1600-1700,
Vilnius, Lithuania, #BuildStuffLT
tomsgilb@gmail.com
@imtomgilb
www.gilb.com
These slides are on gilb.com downloads, and twittered at #BuildstuffLT
The Talk was videoed.
Paper: Value-Driven Development Principles and Values – Agility is the Tool, Not the Master
July 2010 Issue 3, Agile Record 2010 (www.AgileRecord.com)
http://www.gilb.com/tiki-download_file.php?fileId=431
http://www.slideshare.net/tomgilb1/agility-is-the-tool-gilb-vilnius-9-dec-2013
Agile Principles : Agile Record Paper as Published
http://www.gilb.com/tiki-download_file.php?fileId=431
Value-Driven Development Principles and Values – Agility is the Tool, Not the Master
July 2010 Issue 3, Agile Record 2010 (www.AgileRecord.com)
http://www.gilb.com/tiki-download_file.php?fileId=431
Notes: Version Buildstuff Vilnius Dec 9 2013
Might need trimming as I am doing the Case studies in separate talk next day
Slides originated June 7-8 2010 Digerud
It took me on 8th from about 13-21 to finish these from my raw materials
Added (Wright Citi case, and That’s all folks) slides 21 sept 2011 7 Nov 2013
Main Talk vastly upgraded for Agile Warsaw (recorded talk) Oct 2013
Added about 10 Green Week slides at end for Agile Singapore. 7 Nov 2013 Recorded

## Slide 2: Defining ‘Agile’
“Any set of tactics that enable a prioritised stream of useful results, in spite of a changing environment”
      TsG 7 June 2013
A focus on ‘Agile’, is the wrong level of focus.
  Using agile tactics that ‘work’, is a good idea.
Focus on results, no matter what.
As a government minister, I was asked to give ideas to, put it “Value for Money”
Notes: http://www.google.com/imgres?imgurl=http://keepingagile.files.wordpress.com/2012/06/genericagileconceptideogram.png&imgrefurl=http://keeping-agile.com/&h=1088&w=1426&sz=439&tbnid=wlLdDxB_sXa_VM:&tbnh=82&tbnw=108&zoom=1&usg=__XS_KE8RhixHHbCmLa3CJiUKdiHA=&docid=YErwU0C8H4LOJM&sa=X&ei=HSayUaX5CYbj4QTpqoC4Aw&ved=0CFEQ9QEwCg&dur=1002

## Slide 3
3
Copyright: Kai@Gilb.com
Stakeholders
Values
Solutions
Decompose
Develop
Deliver
Measure
Learn
Value Management Process
Notes: Comment: this is the Evo version of an Agile Cycle. But it is a variation on the classic Deming/Shewhart Plan Do Study Act clycle from Statistical Process Control. TSg June 7 2013

## Slide 4
Copyright: Kai@Gilb.com
Copyright: Kai@Gilb.com
Stakeholders
Values
Measure
Learn
Value Management Process
4
Solutions
Decompose
Develop
Deliver
Scrum
Notes: Comment: Scrum or other Agile IT methods, are at best a part of the business solution. They must be managed carefully, and quantitatively so they give real busness results, not just dubious IT systems. TsG June 7 2013

## Slide 5
Agile World View
“Agility” has many dimensions other than IT
It ranges from leadership to technological agility
The focus of this brief is program management agility
F
E
Agile Leaders
Agile Organization Change
Agile Acquisition & Contracting
Agile Strategic Planning
Agile Capability Analysis
Agile Program Management
Agile Tech.
Agile Information Systems
Agile Tools
Agile Processes & Practices
Agile Systems Development
Agile Project Management
5
Source:
David Rico
Notes: Comment: Agile concepts apply to all management processes

## Slide 6
Agile Recap
Agile methods DON’T mean deliver it now & fix it later
Lightweight, yet disciplined approach to development
Reduced cost, risk, & waste while improving quality
6
Rico, D. F. (2012). What’s really happening in agile methods: Its principles revisited? Retrieved June 6, 2012, from http://davidfrico.com/agile-principles.pdf
Rico, D. F. (2012). The promises and pitfalls of agile methods. Retrieved February 6, 2013 from
Rico, D. F. (2012). How do lean & agile intersect? Retrieved February 6, 2013, from http://davidfrico.com/agile-concept-model-3.pdf
What | How | Result
Flexibility | Use lightweight, yet disciplined processes and artifacts | Low work-in-process
Customer | Involve customers early and often throughout development | Early feedback
Prioritize | Identify highest-priority, value-adding business needs | Focus resources
Descope | Descope complex programs by an order of magnitude | Simplify problem
Decompose | Divide the remaining scope into smaller batches | Manageable pieces
Iterate | Implement pieces one at a time over long periods of time | Diffuse risk
Leanness | Architect and design the system one iteration at a time | JIT waste-free design
Swarm | Implement each component in small cross-functional teams | Knowledge transfer
Collaborate | Use frequent informal communications as often as possible | Efficient data transfer
Test Early | Incrementally test each component as it is developed | Early verification
Test Often | Perform system-level regression testing every few minutes | Early validation
Adapt | Frequently identify optimal process and product solutions | Improve performance
E
E
E
E
E
E
E
E
F
F
F
F
F
F
F
F
Source:
David Rico
Notes: Comment: Agile is divide and conquer, bug problems, so we keep contact with reality, our stakeholders, and real results. It is a Cartesian method. Analysis, Mastery, Synthesis.

## Slide 7: 14 PITFALLS OF AGILE METHODS
● Change – Use of top-down, big-bang organization change, adoption, and institutionalization. ● Culture – Agile concepts, practices, and terminology collide with well-entrenched traditional methods.
● Acquisition – Using traditional, fixed-price contracting for large agile delivery contracts and projects.
● Misuse – Scaling up to extremely complex large-scale projects instead of reducing scope and size. ● Organization – Unwillingness to integrate and dissolve testing/QA functional silos and departments.
● Training – Inadequate, insufficient, or non-existent agile training (and availability of agile coaches). ● Infrastructure – Inadequate management and development tools, technologies, and environment. ● Interfacing – Integration with portfolio, architecture, test, quality, security, and usability functions. ● Planning – Inconsistency, ambiguity, and non-standardization of release and iteration planning. ● Trust – Micromanagement, territorialism, and conflict between project managers and developers. ● Teamwork – Inadequate conflict management policies, guidelines, processes, and practices. ● Implementation – Inadequate testing to meet iteration time-box constraints vs. quality objectives. ● Quality - Inconsistent use of agile testing, usability, security, and other cost-effective quality practices.
● Experience - Inadequate skills and experience (or not using subject matter experts and coaches).
(Note. Firms may prematurely "revert" to inexorably slower and more expensive traditional methods or "leap" onto lean methods that may not adequately address common pitfalls of adopting agile methods.)
Source: David Rico http://davidfrico.com/agile-pros-cons.pdf 2012

## Slide 8
Value Driven Scrum
System
Owner
Stakeholders Values
Business Values
Product
Owner
Build
Test
Maintain
Detailed Technical Design
System Functions

## Slide 9: Value Decision Tables
Business Goals | Training Costs | User Productivity
Profit | -10% | 40%
Market Share | 50% | 10%
Resources | 20% | 10%
Stakeholder Val. | Intuitiveness | Performance
Training Costs | -10% | 50 %
User Productivity | 10 % | 10%
Resources | 2 % | 5 %
Product Values | GUI Style Rex | Code Optimize
Intuitiveness | -10% | 40%
Performance | 50% | 80 %
Resources | 1 % | 2 %
Prioritized List
1. Code Optimize
2. Solution 9
3. Solution 7
We measure improvements
Learn and Repeat
Copyright: Kai@Gilb.com
Scrum Develops
Jeffsutherland Twitter: Very cool product backlog management
by Tom and Kai Gilb http://ad.vu/2h4d Sat 28 March 2009
Notes: developing a large web portal www.bring.no dk/se/nl/co.uk/com/ee at Posten Norge
Jeffsutherland Twitter: Very cool product backlog management
by Tom and Kai Gilb http://ad.vu/2h4d Sat 28 March 2009

## Slide 10
10
Copyright: Kai@Gilb.com
Jeffsutherland Twitter: Very cool product backlog management
by Tom and Kai Gilb http://ad.vu/2h4d Sat 28 March 2009
Notes: developing a large web portal www.bring.no dk/se/nl/co.uk/com/ee at Posten Norge
Photo Kai 2009 at OC4 Kolbotn w Jeff
Photo Sutherland 2010 April from Digerud Cabin

## Slide 11: Gilb’s Ten Key Agile Principles to avoid bureaucracy and give creative freedom (see Polish & Eng. Paper on this! ) Core, Agilerecord.com, Gilb.com
1. Control projects by quantified critical-few results. 1 Page total !
  (not stories, functions, features, use cases, objects, ..)
2. Make sure those results are business results, not technical
  Align your project with your financial sponsor’s interests!
3. Give developers freedom, to find out how to deliver those results
4. Estimate the impacts of your designs, on your quantified goals
5. Select designs with the best impacts in relation to their costs, do them first.
6. Decompose the workflow, into weekly (or 2% of budget) time boxes
7. Change designs, based on quantified experience of implementation
8. Change requirements, based in quantified experience, new inputs
9. Involve the stakeholders, every week, in setting quantified goals
10. Involve the stakeholders, every week, in actually using increments
Copyright 2004-13 Gilb, may be used citing source
Notes: Created Thursday, November 25, 2004 during XP conf London lecture by Tom@Gilb.com
Photo taken at Art of Living Ashram Bad Antogast Germancy June 2003, in file tom photos miniatures and in ARL iphoto subfile

## Slide 12: Gilb’s Agile Principles to avoid bureaucracy and give creative freedom (1 sentence summary)
Main Idea:
Get early, and frequent, real, stakeholder net-value - delivered
Deliver
Value !
Notes: Created Thursday, November 25, 2004 during XP conf London lecture by Tom@Gilb.com
Photo taken at Art of Living Ashram Bad Antogast Germancy June 2003, in file tom photos miniatures and in AOL iphoto subfile

## Slide 13: 1. Control projects by quantified critical-few results. 1 Page total !
  (not stories, functions, features, use cases, objects, ..)
Notes: http://www.hit.nl/images/content/BSCStrategyMap.png

## Slide 14: NOT LIKE THIS! Project Objectives ‘Unquantified few’
Defined Scales of Measure:
  Demands comparative thinking.
  Leads to requirements that are unambiguously clear
  Helps Team be Aligned with the Business
1. Central to The Corporations business strategy is to be the world’s premier integrated <domain> service provider.
2. Will provide a much more efficient user experience
3. Dramatically scale back the time frequently needed after the last data is acquired to time align, depth correct, splice, merge, recompute and/or do whatever else is needed to generate the desired products
4. Make the system much easier to understand and use than has been the case for previous system.
5. A primary goal is to provide a much more productive system development environment than was previously the case.
6. Will provide a richer set of functionality for supporting next-generation logging tools and applications.
7. Robustness is an essential system requirement (see rewrite in example below)
8. Major improvements in data quality over current practices
Real Example of Lack of CLARITY
This lack of clarity cost them $100,000, 000
Notes: http://www.chariho.k12.ri.us/curriculum/MIsmart/matter/matter.html

## Slide 15: More like this! (Real Example).
<- Business
Objectives
Quantified

## Slide 16: Real EXAMPLE of Objectives/Strategy definitions US Army Example: PERSINSCOM: Personnel System
Example of one of the Objectives:
Customer Service:
Type: Critical Top level Systems Objective
Gist: Improve customer perception of quality of service provided.
Scale: Violations of Customer Agreement per Month.
Meter: Log of Violations.
Past [Last Year] Unknown Number State of PERSCOM Management Review
Record [NARDAC] 0 ?  NARDAC Reports Last Year
Fail : <must be better than Past, Unknown number> CG
Goal [This Year, PERSINCOM] 0 “Go for the Record”  Group SWAG
.

## Slide 17: Principle 2. Make sure those results are business results, not JUST technical
  Align your project with your financial sponsor’s interests!
Notes: http://dashboardsbyexample.com/wp-content/uploads/2008/06/marketing-spend-business-results-model.png

## Slide 18: The Strategic Objectives (CTO level) Example from Ericsson Base Stations
5
    the Fundamental Objectives (Profit, survival)
    Software Productivity:
      Lines of Code Generation Ability
    Lead-Time:
    Predictability.
    TTMP: Predictability of Time To Market:
    Product Attributes:
    Customer Satisfaction:
    Profitability:
Productivity Slides incl Ericsson
http://www.gilb.com/dl559
Notes: 5
http://www.thectoforum.com/images/CTO_web-2.jpg

## Slide 19: ‘Means’ Objectives which support Strategic Objectives: all quantified in practice, see URL below
6
  Support the Strategic Objectives
    Complaints:
    Feature Production:
    Rework Costs:
    Installation Ability:
    Service Costs:
    Training Costs:
    Specification Defectiveness:
    Specification Quality:
    Improvement ROI:
"Let no man turn aside,
ever so slightly,
from the broad path of honour,
on the plausible pretence
that he is justified by the goodness
of his end.
All good ends can be worked out
by good means." Charles Dickens
Productivity Slides incl Ericsson
http://www.gilb.com/dl559
Notes: 6

## Slide 20: Simple Product Owner (Ambler)
http://www.agilemodeling.com/essays/productOwner.htm
Notes: Made tsg Vilnius 9 dec 2013

## Slide 21: ‘Advanced Product Owner’ Policy: System ‘Requirements Engineer’ (RE).
  Background: this policy defines the expectations for a ‘Product Owner’ (PO) for serious, critical, large, and complex systems.
    1. This implies that it is not enough to manage a simple stream (Backlog) of ‘user stories’ fed to a programming team.
    2. It is necessary to communicate with a systems engineering team, developing or maintaining the ‘Product’.
      System implies management of all technological components, people, data, hardware, organization, training, motivation, and programs.
      Engineering: means systematic and quantified, ‘real’ engineering processes, where proactive design is used to manage system performance (incl. all qualities) attributes and costs.
New idea being drafted by TG for a Client Bank, 7.12.2013
Notes: ‘Advanced Product Owner’ Policy: System ‘Requirements Engineer’ (RE).
  Background: this policy defines the expectations for a ‘Product Owner’ (PO) for serious, critical, large, and complex systems.
    This implies that it is not enough to manage a simple stream (Backlog) of ‘user stories’ fed to a programming team.
    It is necessary to communicate with a systems engineering team, developing or maintaining the ‘Product’.
      System implies management of all technological components, people, data, hardware, organization, training, motivation, and programs.
      Engineering: means systematic and quantified, ‘real’ engineering processes, where proactive design is used to manage system performance (incl. all qualities) attributes and costs.
1. COMPLETE REQUIREMENTS:
  The RE (Requirements Engineer) is responsible for absolutely all requirements specification that the system must be aware of, and be responsible for to all critical or relevant stakeholders.
    In particular, the RE is not narrowly responsible for requirements from users and customers alone. They are responsible for all other stakeholders, such as operations, maintenance, laws, regulations, resource providers, and more.
2. QUALITY REQUIREMENTS:
  The RE is responsible for the quality level, in relation to official standards, of all requirements they transmit to others.
    They are consequently responsible for making sure the quality of incoming raw requirements, needs, values, constraints etc. is good enough to process. No GIGO.
    If input is not good quality, they are responsible for making sure it is better quality, or at least clearly annotated where there is doubt, incompleteness, ambiguity and any other potential problems, they cannot resolve yet.
3. ARCHITECTURE:
  The Requirements Engineer is NOT responsible for any architecture or design process itself. This will be done by professional engineers and architects.
  They are however very much responsible for a complete and intelligible quality set of requirements, transmitted to the designers and architects.
  The are also responsible for transmitting quality-controlled architecture or design specifications to any relevant system builders. These are the designs which are input requirements to builders. Effectively they are ‘design constraints requirements’.
4. Priority Information:
  The Requirements Engineer is NOT responsible for prioritization of requirements.
  Prioritization is done dynamically at the project management (PM) level, based on prioritization signals in the requirements, and on current feedback and experience in the value delivery cycles (Sprints).
  The primary responsibility of the Requirements Engineer, is to systematically and thoroughly collect and disseminate all relevant priority signals, into the requirement specification; so that intelligent prioritization can be done at any relevant level, and at any time.

## Slide 22: ‘Advanced Product Owner’ Policy: System ‘Requirements Engineer’ (RE).
1. COMPLETE REQUIREMENTS:
  The RE (Requirements Engineer) is responsible for absolutely all requirements specification that the system must be aware of, and be responsible for to all critical or relevant stakeholders.
    In particular, the RE is not narrowly responsible for requirements from users and customers alone. They are responsible for all other stakeholders, such as operations, maintenance, laws, regulations, resource providers, and more.
2. QUALITY REQUIREMENTS:
  The RE is responsible for the quality level, in relation to official standards, of all requirements they transmit to others.
    They are consequently responsible for making sure the quality of incoming raw requirements, needs, values, constraints etc. is good enough to process. No GIGO.
    If input is not good quality, they are responsible for making sure it is better quality, or at least clearly annotated where there is doubt, incompleteness, ambiguity and any other potential problems, they cannot resolve yet.
3. ARCHITECTURE:
  The Requirements Engineer is NOT responsible for any architecture or design process itself. This will be done by professional engineers and architects.
  They are however very much responsible for a complete and intelligible quality set of requirements, transmitted to the designers and architects.
  The are also responsible for transmitting quality-controlled architecture or design specifications to any relevant system builders. These are the designs which are input requirements to builders. Effectively they are ‘design constraints requirements’.
4. PRIORITY INFORMATION:
  The Requirements Engineer is NOT responsible for prioritization of requirements.
  Prioritization is done dynamically at the project management (PM) level, based on prioritization signals in the requirements, and on current feedback and experience in the value delivery cycles (Sprints).
  The primary responsibility of the Requirements Engineer, is to systematically and thoroughly collect and disseminate all relevant priority signals, into the requirement specification; so that intelligent prioritization can be done at any relevant level, and at any time.
New idea being drafted by TG for a Client Bank, 7.12.2013
Notes: Dec 9 2013
‘Advanced Product Owner’ Policy: System ‘Requirements Engineer’ (RE).
  Background: this policy defines the expectations for a ‘Product Owner’ (PO) for serious, critical, large, and complex systems.
    This implies that it is not enough to manage a simple stream (Backlog) of ‘user stories’ fed to a programming team.
    It is necessary to communicate with a systems engineering team, developing or maintaining the ‘Product’.
      System implies management of all technological components, people, data, hardware, organization, training, motivation, and programs.
      Engineering: means systematic and quantified, ‘real’ engineering processes, where proactive design is used to manage system performance (incl. all qualities) attributes and costs.
1. COMPLETE REQUIREMENTS:
  The RE (Requirements Engineer) is responsible for absolutely all requirements specification that the system must be aware of, and be responsible for to all critical or relevant stakeholders.
    In particular, the RE is not narrowly responsible for requirements from users and customers alone. They are responsible for all other stakeholders, such as operations, maintenance, laws, regulations, resource providers, and more.
2. QUALITY REQUIREMENTS:
  The RE is responsible for the quality level, in relation to official standards, of all requirements they transmit to others.
    They are consequently responsible for making sure the quality of incoming raw requirements, needs, values, constraints etc. is good enough to process. No GIGO.
    If input is not good quality, they are responsible for making sure it is better quality, or at least clearly annotated where there is doubt, incompleteness, ambiguity and any other potential problems, they cannot resolve yet.
3. ARCHITECTURE:
  The Requirements Engineer is NOT responsible for any architecture or design process itself. This will be done by professional engineers and architects.
  They are however very much responsible for a complete and intelligible quality set of requirements, transmitted to the designers and architects.
  The are also responsible for transmitting quality-controlled architecture or design specifications to any relevant system builders. These are the designs which are input requirements to builders. Effectively they are ‘design constraints requirements’.
4. Priority Information:
  The Requirements Engineer is NOT responsible for prioritization of requirements.
  Prioritization is done dynamically at the project management (PM) level, based on prioritization signals in the requirements, and on current feedback and experience in the value delivery cycles (Sprints).
  The primary responsibility of the Requirements Engineer, is to systematically and thoroughly collect and disseminate all relevant priority signals, into the requirement specification; so that intelligent prioritization can be done at any relevant level, and at any time.

## Slide 23: Product Owner at Scale (Ambler)
http://www.agilemodeling.com/essays/productOwner.htm
Notes: Made tsg Vilnius 9 dec 2013

## Slide 24: 3. Give developers freedom, to find out how to deliver those results
Notes: http://www.treehugger.com/zaha-hadad-car.jpg

## Slide 25: Principle 4. Estimate the impacts of your designs, on your quantified goals
If you cannot, then your knowledge is of a meagre and unsatisfactory kind (Lord Kelvin)
Notes: http://www.ie.sogeti.com/PageFiles/877/Impact%20six%20themes%20%5B1%5D.gif

## Slide 26: Quantified Value Delivery Project Management in a Nutshell (Confirmit Case, Norway) Quantified Value Requirements, Design, Design Value/cost estimation, Measurement of Value Delivery, Incremental Project Progress to Date
Cumulative
weekly
progress
metric
Priority
Next week
Warning
metrics based
Constraint
Target
Estimates
Weekly
Testing

## Slide 27: REAL EXAMPLE: Strategy Impact Estimation: for a $100,000,000 Organizational Improvement Investment
Cost
Benefit/Cost
ratio
Technical Strategies
Objectives
Strategy
Impacts
on
Objectives
"Benefits"
358 !
Notes: http://www.rainforestfoundationuk.org/s-Trail%202%20-%20Hunting%20in%20the%20Rainforest
Figure 2: an ‘Impact Estimation Table’ (see ‘CE’ book) A set of 12 proposed Engineering Processes, with about $100,000,000 in total investment projected over time, are evaluated theoretically for their impact on 13 business objectives (defined in Fig. 1 above).

## Slide 28: 5. Select designs with the best impacts in relation to their costs, do them first.
Notes: http://bellagio.typepad.com/main/images/vaccine_priority_groups.jpg

## Slide 29: Impact Estimation: Value Decision Table Decomposes Architecture by Value, and Value/Cost “Efficiency”
29.5:1
Notes: 29.5 to 1 fixed and 2 rectangles moved to right 12 3 2013 stockholm
Arrows and heqader edited Dec 9 2013 Vilnius TG

## Slide 30: Principle 6. Decompose the workflow, into weekly (or 2% of budget) time boxes
Decomposition of Projects: How to Design Small Incremental Steps INCOSE 2008
http://www.gilb.com/tiki-download_file.php?fileId=41
Notes: http://www.agileadvice.com/archives/IterationValueDelivery.png

## Slide 31: 1 1 1 1 1 1 Unity
  1% increase at least
  1 stakeholder
  1 quality or value
  1-week delivery cycle
  1 function focus
  1 design used
http://www.gilb.com/tiki-download_file.php?fileId=451
111111 Unity Method slides
Notes: Decomposition of Projects - How to design small incremental result steps, 2008 Paper
http://www.gilb.com/tiki-download_file.php?fileId=41
111111 Unity Method of Decomposition into weekly increments of value delivery. (10 min slides)
http://www.gilb.com/tiki-download_file.php?fileId=451
Draft 11 dec 2008 7MB see paper on it at [http://www.gilb.com/tiki-download_file.php?fileId=41]
Note a raw set of slides not well sorted or refined but a beginning set for a 1 day course on decomposition, aimed perhaps at Scrum and Agile people
http://www.gilb.com/tiki-download_file.php?fileId=350
Decomposition of Projects: How to Design Small Incremental Steps INCOSE 2008
http://www.gilb.com/tiki-download_file.php?fileId=41
http://www.gilb.com/tiki-download_file.php?fileId=350
Decomposition Slides Aug 2010
http://www.gilb.com/tiki-download_file.php?fileId=451
111111 Unity Method slides 10 minute Talk
Evo Paper
Slides

## Slide 32: Decomposition Principles A Teachable Discipline
How to decompose systems into small evolutionary steps:
some principles to apply:
1• Believe there is a way to do it, you just have not found it yet!
2• Identify obstacles, but don't use them as excuses: use your imagination to get rid of them!
3• Focus on some usefulness for the user or customer, however small.
4• Do not focus on the design ideas themselves, they are distracting, especially for small initial cycles. Sometimes you have to ignore them entirely in the short term!
5• Think; one customer, tomorrow, one interesting improvement.
6• Focus on the results (which you should have defined in your goals, moving toward target levels).
7• Don't be afraid to use temporary-scaffolding designs. Their cost must be seen in the light of the value of making some progress, and getting practical experience.
8• Don't be worried that your design is inelegant; it is results that count, not style.
9• Don't be afraid that the customer won't like it. If you are focusing on results they want, then by definition, they should like it. If you are not, then do!
10• Don't get so worried about "what might happen afterwards" that you can make no practical progress.
11• You cannot foresee everything. Don't even think about it!
12• If you focus on helping your customer in practice, now, where they really need it, you will be forgiven a lot of ‘sins’!
13• You can understand things much better, by getting some practical experience (and removing some of your fears).
14• Do early cycles, on willing local mature parts of your user community.
15• When some cycles, like a purchase-order cycle, take a long time, initiate them early, and do other useful cycles while you wait.
16• If something seems to need to wait for ‘the big new system’, ask if you cannot usefully do it with the ‘awful old system’, so as to pilot it realistically, and perhaps alleviate some 'pain' in the old system.
17• If something seems too costly to buy, for limited initial use, see if you can negotiate some kind of ‘pay as you really use’ contract. Most suppliers would like to do this to get your patronage, and to avoid competitors making the same deal.
18• If you can't think of some useful small cycles, then talk directly with the real ‘customer’ or end user. They probably have dozens of suggestions.
19• Talk with end users in any case, they have insights you need.
20• Don't be afraid to use the old system and the old ‘culture’ as a launching platform for the radical new system. There is a lot of merit in this, and many people overlook it.
I have never seen an exception in 33 years of doing this with many varied cultures. Oh Ye of little faith!
http://www.gilb.com/tiki-download_file.php?fileId=41
Notes: Decomposition of Projects: How to Design Small Incremental Steps INCOSE 2008
http://www.gilb.com/tiki-download_file.php?fileId=41
http://www.gilb.com/tiki-download_file.php?fileId=350
Decomposition Slides Aug 2010

## Slide 33: Rene Descartes on Focus
“We should bring the whole force of our minds
  to bear upon the most minute and simple details
  and to dwell upon them for a long time
  so that we become accustomed to perceive the truth clearly and distinctly.”
Rene Descartes, Rules for the Direction of the Mind, 1628
Notes: Added January 5 2003 TG from quotations from Ben Shneiderman
url www.cals.ncsu.edu for Descartes
Rene Descartes was a mediocre scientist, a great mathematician and an even greater philosopher. He is considered to be the father of modern philosophy. His thought affected educational theory in the following manner:
1. EDUCATION A NATURAL RIGHT OF MAN. Since knowledge is attained through the reasoning processes, every man has the right to develop the innate faculties of his soul. Although men learn at different paces, education is possible for all.
2. IMPORTANCE OF DOUBTING AUTHORITATIVE PROPOSITIONS. It is necessary for man to doubt everything prior to asserting any definite truths. This act of doubt leads the mind to the rational assertion of a self-evident principle that cannot be doubted. Therefore, it is possible to infer the right of each man to think for himself.
3. CLEAR AND CERTAIN TRUTHS. Man ought to accept no statement as true, unless it appears clear and certain to his intellect.
4. PSYCHOLOGICAL PRINCIPLES OF KNOWLEDGE. In the act of knowing, the mind proceeds from what is already known to the unknown, This infers the need for a teacher to base learning upon the intellectual experience of each pupil. Descartes asserted the principle that the mind moves from the concrete to the abstract, the simple to the more complex. These principles underlie the organization of

## Slide 34: Tao Te Ching (500BC)
That which remains quiet, is easy to handle.
That which is not yet developed is easy to manage.
That which is weak is easy to control.
That which is still small is easy to direct.
Deal with little troubles before they become big.
Attend to little problems before they get out of hand.
  For the largest tree was once a sprout,
the tallest tower started with the first brick,
and the longest journey started with the first step.
  From Lao Tzu in Bahn, 1980 (also quoted in Gilb, Principles of Software Engineering Management page 96), Penguin book
Notes: lao_tzu_tao_te_ching.jpg
355 × 400 - Tao Te Ching ...
bodymindheartspirit.ning.com
Similar ‑ More sizes
Website for this image
edepot.com
daodejing1.jpg
350 × 467 - Tao and First Line of Tao Te Ching
edepot.com

## Slide 35: Principle 7. Change designs, based on quantified experience of implementation
Design is the servant of the requirement. If it does not work
‘fire’ it.
Notes: http://blogs.warwick.ac.uk/images/eludlow/2007/06/20/modepaleizen04_groot.jpghttp://blogs.warwick.ac.uk/images/eludlow/2007/06/20/modepaleizen04_groot.jpg

## Slide 36: Lean Startup: High Unknowns
http://www.slideshare.net/venturehacks/the-lean-startup-2
Notes: Source
http://www.slideshare.net/venturehacks/the-lean-startup-2
  Slides bySteven Blank and Eric Ries. “The Lean Startup, Low Burn by Design , not Crisis”

## Slide 37: Value Management (Gilb, Evo)
37
Copyright: Kai@Gilb.com
Notes: From Kai Gilb
Bring Case (gilb.com)
www.gilb.com/tiki-download_file.php?fileId=277

## Slide 38: 20 Sept, 2011 Report on Gilb Evo method (Richard Smith, Citigroup)
http://rsbatechnology.co.uk/blog:8
Back in 2004, I was employed by a large investment bank in their FX e-commerce IT department as a business analyst.
The wider IT organisation used a complex waterfall-based project methodology that required use of an intranet application to manage and report progress.
However, it's main failings were that it almost totally missed the ability to track delivery of actual value improvements to a project's stakeholders, and the ability to react to changes in requirements and priority for the project's duration.
The toolset generated lots of charts and stats that provided the illusion of risk control. but actually provided very little help to the analysts, developers and testers actually doing the work at the coal face.
The proof is in the pudding;
  I have used Evo (albeit in disguise sometimes) on two large, high-risk projects in front-office investment banking businesses, and several smaller tasks.
  On the largest critical project, the original business functions & performance objective requirements document, which included no design, essentially remained unchanged over the 14 months the project took to deliver,
  but the detailed designs (of the GUI, business logic, performance characteristics) changed many many times, guided by lessons learnt and feedback gained by delivering a succession of early deliveries to real users.
  In the end, the new system responsible for 10s of USD billions of notional risk, successfully went live over one weekend for 800 users worldwide, and was seen as a big success by the sponsoring stakeholders.
“ I attended a 3-day course with you and Kai whilst at Citigroup in 2006”
Notes: Yes, Richard was trained in Requirements by you and Kai while he was at Citi.
From: Tom Gilb [mailto:tom@gilb.com]
Sent: 26 February 2009 15:16
To: Dick Holland
Hi Tom,
I am honoured to be in contact with you again! I attended a 3-day course with you and Kai whilst at Citigroup in 2006 (I worked in the FX e-commerce front-office team at the time). You may be interested to know that I wrote a detailed business requirements spec (no design, just requirements) adopting many of your ideas shortly after the course including key quantified requirements. This spec ended up staying largely stable for a year as we did an evo – like development process, at the end of which we successfully went live with a brand-new FX order management system in a global big-bang release to 800 Citi users in 20 locations.
I hope to continue to use and expand competitive engineering practises at my new home here at LZ, with Dick’s help!
Many regards,
Richard.
Hi Tom,
Thought you might like to know I have just completed a review of Competitive Engineering on my own company's blog:
http://rsbatechnology.co.uk/blog:8
As I tried to do when I worked with Dick at LatentZero, I continue to try and spread the word to a world of (initial) unbelievers! I actually have an interesting opportunity right now to demonstrate the benefits of early & often delivery of value to stakeholders in a couple of new projects. Look forward to meeting you and Kai again sometime ...
Regards,
Richard Smith.sept 10 2011

## Slide 39: Dynamic (Agile, Evo) design testing: not unlike ‘Lean Startup’
“… but the detailed designs
  (of the GUI, business logic, performance characteristics)
changed many many times,
guided by lessons learnt
and feedback gained by
delivering a succession of early deliveries
to real users”
“ I attended a 3-day course with you and Kai whilst at Citigroup in 2006”, Richard Smith
Richard Smith
Notes: Yes, Richard was trained in Requirements by you and Kai while he was at Citi.
From: Tom Gilb [mailto:tom@gilb.com]
Sent: 26 February 2009 15:16
To: Dick Holland
Hi Tom,
I am honoured to be in contact with you again! I attended a 3-day course with you and Kai whilst at Citigroup in 2006 (I worked in the FX e-commerce front-office team at the time). You may be interested to know that I wrote a detailed business requirements spec (no design, just requirements) adopting many of your ideas shortly after the course including key quantified requirements. This spec ended up staying largely stable for a year as we did an evo – like development process, at the end of which we successfully went live with a brand-new FX order management system in a global big-bang release to 800 Citi users in 20 locations.
I hope to continue to use and expand competitive engineering practises at my new home here at LZ, with Dick’s help!
Many regards,
Richard.
Hi Tom,
Thought you might like to know I have just completed a review of Competitive Engineering on my own company's blog:
http://rsbatechnology.co.uk/blog:8
As I tried to do when I worked with Dick at LatentZero, I continue to try and spread the word to a world of (initial) unbelievers! I actually have an interesting opportunity right now to demonstrate the benefits of early & often delivery of value to stakeholders in a couple of new projects. Look forward to meeting you and Kai again sometime ...
Regards,
Richard Smith.sept 10 2011

## Slide 40: Quinnan: IBM FSD Cleanroom Dynamic Design to Cost
Quinnan describes the process control loop used by IBM FSD to ensure that cost targets are met.
'Cost management. . . yields valid cost plans linked to technical performance. Our practice carries cost management farther by introducing design-to-cost guidance. Design, development, and managerial practices are applied in an integrated way to ensure that software technical management is consistent with cost management. The method [illustrated in this book by Figure 7.10] consists of developing a design, estimating its cost, and ensuring that the design is cost-effective.' (p. 473)
He goes on to describe a design iteration process trying to meet cost targets by either redesign or by sacrificing 'planned capability.' When a satisfactory design at cost target is achieved for a single increment, the 'development of each increment can proceed concurrently with the program design of the others.'
'Design is an iterative process in which each design level is a refinement of the previous level.' (p. 474)
It is clear from this that they avoid the big bang cost estimation approach. Not only do they iterate in seeking the appropriate balance between cost and design for a single increment, but they iterate through a series of increments, thus reducing the complexity of the task, and increasing the probability of learning from experience, won as each increment develops, and as the true cost of the increment becomes a fact.
'When the development and test of an increment are complete, an estimate to complete the remaining increments is computed.' (p. 474)
Source: Robert E. Quinnan, 'Software Engineering Management Practices', IBM Systems Journal, Vol. 19, No. 4, 1980, pp. 466~77
This text is cut from Gilb: The Principles of Software Engineering Management, 1988
Notes: Slide developed Oct 6 2013 tsg for London Software Architecture Conference Talk 9 Oct 2013
15.1.18 Quinnan
Source: Robert E. Quinnan, 'Software Engineering Management Practices', IBM Systems Journal, Vol. 19, No. 4, 1980, pp. 466~77
Robert E. Quinnan: The Management of Software Engineering. Part V: Software Engineering Management Practices. IBM Systems Journal 19(4): 466-477 (1980)
Quinnan describes the process control loop used by IBM FSD to ensure that cost targets are met.
'Cost management. . . yields valid cost plans linked to technical performance. Our practice carries cost management farther by introducing design-to-cost guidance. Design, development, and managerial practices are applied in an integrated way to ensure that software technical management is consistent with cost management. The method [illustrated in this book by Figure 7.10] consists of developing a design, estimating its cost, and ensuring that the design is cost-effective.' (p. 473)
He goes on to describe a design iteration process trying to meet cost targets by either redesign or by sacrificing 'planned capability.' When a satisfactory design at cost target is achieved for a single increment, the 'development of each increment can proceed concurrently with the program design of the others.'
'Design is an iterative process in which each design level is a refinement of the previous level.' (p. 474)
It is clear from this that they avoid the big bang cost estimation approach. Not only do they iterate in seeking the appropriate balance between cost and design for a single increment, but they iterate through a series of increments, thus reducing the complexity of the task, and increasing the probability of learning from experience, won as each increment develops, and as the true cost of the increment becomes a fact.
'When the development and test of an increment are complete, an estimate to complete the remaining increments is computed.' (p. 474)
This article is far richer than our few selected quotations can show, with regard to concepts of cost estimation and control.

## Slide 41: Quinnan: IBM FSD Cleanroom Dynamic Design to Cost
Quinnan describes the process control loop used by IBM FSD to ensure that cost targets are met.
'Cost management. . . yields valid cost plans linked to technical performance. Our practice carries cost management farther by introducing design-to-cost guidance. Design, development, and managerial practices are applied in an integrated way to ensure that software technical management is consistent with cost management. The method [illustrated in this book by Figure 7.10] consists of developing a design, estimating its cost, and ensuring that the design is cost-effective.' (p. 473)
He goes on to describe a design iteration process trying to meet cost targets by either redesign or by sacrificing 'planned capability.' When a satisfactory design at cost target is achieved for a single increment, the 'development of each increment can proceed concurrently with the program design of the others.'
'Design is an iterative process in which each design level is a refinement of the previous level.' (p. 474)
It is clear from this that they avoid the big bang cost estimation approach. Not only do they iterate in seeking the appropriate balance between cost and design for a single increment, but they iterate through a series of increments, thus reducing the complexity of the task, and increasing the probability of learning from experience, won as each increment develops, and as the true cost of the increment becomes a fact.
'When the development and test of an increment are complete, an estimate to complete the remaining increments is computed.' (p. 474)
Source: Robert E. Quinnan, 'Software Engineering Management Practices', IBM Systems Journal, Vol. 19, No. 4, 1980, pp. 466~77
This text is cut from Gilb: The Principles of Software Engineering Management, 1988
of developing a design, estimating its cost, and ensuring that the design is cost-effective
Notes: Slide developed Oct 6 2013 tsg for London Software Architecture Conference Talk 9 Oct 2013
15.1.18 Quinnan
Source: Robert E. Quinnan, 'Software Engineering Management Practices', IBM Systems Journal, Vol. 19, No. 4, 1980, pp. 466~77
Robert E. Quinnan: The Management of Software Engineering. Part V: Software Engineering Management Practices. IBM Systems Journal 19(4): 466-477 (1980)
Quinnan describes the process control loop used by IBM FSD to ensure that cost targets are met.
'Cost management. . . yields valid cost plans linked to technical performance. Our practice carries cost management farther by introducing design-to-cost guidance. Design, development, and managerial practices are applied in an integrated way to ensure that software technical management is consistent with cost management. The method [illustrated in this book by Figure 7.10] consists of developing a design, estimating its cost, and ensuring that the design is cost-effective.' (p. 473)
He goes on to describe a design iteration process trying to meet cost targets by either redesign or by sacrificing 'planned capability.' When a satisfactory design at cost target is achieved for a single increment, the 'development of each increment can proceed concurrently with the program design of the others.'
'Design is an iterative process in which each design level is a refinement of the previous level.' (p. 474)
It is clear from this that they avoid the big bang cost estimation approach. Not only do they iterate in seeking the appropriate balance between cost and design for a single increment, but they iterate through a series of increments, thus reducing the complexity of the task, and increasing the probability of learning from experience, won as each increment develops, and as the true cost of the increment becomes a fact.
'When the development and test of an increment are complete, an estimate to complete the remaining increments is computed.' (p. 474)
This article is far richer than our few selected quotations can show, with regard to concepts of cost estimation and control.

## Slide 42: Quinnan: IBM FSD Cleanroom Dynamic Design to Cost
Quinnan describes the process control loop used by IBM FSD to ensure that cost targets are met.
'Cost management. . . yields valid cost plans linked to technical performance. Our practice carries cost management farther by introducing design-to-cost guidance. Design, development, and managerial practices are applied in an integrated way to ensure that software technical management is consistent with cost management. The method [illustrated in this book by Figure 7.10] consists of developing a design, estimating its cost, and ensuring that the design is cost-effective.' (p. 473)
He goes on to describe a design iteration process trying to meet cost targets by either redesign or by sacrificing 'planned capability.' When a satisfactory design at cost target is achieved for a single increment, the 'development of each increment can proceed concurrently with the program design of the others.'
'Design is an iterative process in which each design level is a refinement of the previous level.' (p. 474)
It is clear from this that they avoid the big bang cost estimation approach. Not only do they iterate in seeking the appropriate balance between cost and design for a single increment, but they iterate through a series of increments, thus reducing the complexity of the task, and increasing the probability of learning from experience, won as each increment develops, and as the true cost of the increment becomes a fact.
'When the development and test of an increment are complete, an estimate to complete the remaining increments is computed.' (p. 474)
Source: Robert E. Quinnan, 'Software Engineering Management Practices', IBM Systems Journal, Vol. 19, No. 4, 1980, pp. 466~77
This text is cut from Gilb: The Principles of Software Engineering Management, 1988
iteration process trying to meet cost targets by either redesign or by sacrificing 'planned capability’
Notes: Slide developed Oct 6 2013 tsg for London Software Architecture Conference Talk 9 Oct 2013
15.1.18 Quinnan
Source: Robert E. Quinnan, 'Software Engineering Management Practices', IBM Systems Journal, Vol. 19, No. 4, 1980, pp. 466~77
Robert E. Quinnan: The Management of Software Engineering. Part V: Software Engineering Management Practices. IBM Systems Journal 19(4): 466-477 (1980)
Quinnan describes the process control loop used by IBM FSD to ensure that cost targets are met.
'Cost management. . . yields valid cost plans linked to technical performance. Our practice carries cost management farther by introducing design-to-cost guidance. Design, development, and managerial practices are applied in an integrated way to ensure that software technical management is consistent with cost management. The method [illustrated in this book by Figure 7.10] consists of developing a design, estimating its cost, and ensuring that the design is cost-effective.' (p. 473)
He goes on to describe a design iteration process trying to meet cost targets by either redesign or by sacrificing 'planned capability.' When a satisfactory design at cost target is achieved for a single increment, the 'development of each increment can proceed concurrently with the program design of the others.'
'Design is an iterative process in which each design level is a refinement of the previous level.' (p. 474)
It is clear from this that they avoid the big bang cost estimation approach. Not only do they iterate in seeking the appropriate balance between cost and design for a single increment, but they iterate through a series of increments, thus reducing the complexity of the task, and increasing the probability of learning from experience, won as each increment develops, and as the true cost of the increment becomes a fact.
'When the development and test of an increment are complete, an estimate to complete the remaining increments is computed.' (p. 474)
This article is far richer than our few selected quotations can show, with regard to concepts of cost estimation and control.

## Slide 43: Quinnan: IBM FSD Cleanroom Dynamic Design to Cost
Quinnan describes the process control loop used by IBM FSD to ensure that cost targets are met.
'Cost management. . . yields valid cost plans linked to technical performance. Our practice carries cost management farther by introducing design-to-cost guidance. Design, development, and managerial practices are applied in an integrated way to ensure that software technical management is consistent with cost management. The method [illustrated in this book by Figure 7.10] consists of developing a design, estimating its cost, and ensuring that the design is cost-effective.' (p. 473)
He goes on to describe a design iteration process trying to meet cost targets by either redesign or by sacrificing 'planned capability.' When a satisfactory design at cost target is achieved for a single increment, the 'development of each increment can proceed concurrently with the program design of the others.'
'Design is an iterative process in which each design level is a refinement of the previous level.' (p. 474)
It is clear from this that they avoid the big bang cost estimation approach. Not only do they iterate in seeking the appropriate balance between cost and design for a single increment, but they iterate through a series of increments, thus reducing the complexity of the task, and increasing the probability of learning from experience, won as each increment develops, and as the true cost of the increment becomes a fact.
'When the development and test of an increment are complete, an estimate to complete the remaining increments is computed.' (p. 474)
Source: Robert E. Quinnan, 'Software Engineering Management Practices', IBM Systems Journal, Vol. 19, No. 4, 1980, pp. 466~77
This text is cut from Gilb: The Principles of Software Engineering Management, 1988
Design is an iterative process
Notes: Slide developed Oct 6 2013 tsg for London Software Architecture Conference Talk 9 Oct 2013
15.1.18 Quinnan
Source: Robert E. Quinnan, 'Software Engineering Management Practices', IBM Systems Journal, Vol. 19, No. 4, 1980, pp. 466~77
Robert E. Quinnan: The Management of Software Engineering. Part V: Software Engineering Management Practices. IBM Systems Journal 19(4): 466-477 (1980)
Quinnan describes the process control loop used by IBM FSD to ensure that cost targets are met.
'Cost management. . . yields valid cost plans linked to technical performance. Our practice carries cost management farther by introducing design-to-cost guidance. Design, development, and managerial practices are applied in an integrated way to ensure that software technical management is consistent with cost management. The method [illustrated in this book by Figure 7.10] consists of developing a design, estimating its cost, and ensuring that the design is cost-effective.' (p. 473)
He goes on to describe a design iteration process trying to meet cost targets by either redesign or by sacrificing 'planned capability.' When a satisfactory design at cost target is achieved for a single increment, the 'development of each increment can proceed concurrently with the program design of the others.'
'Design is an iterative process in which each design level is a refinement of the previous level.' (p. 474)
It is clear from this that they avoid the big bang cost estimation approach. Not only do they iterate in seeking the appropriate balance between cost and design for a single increment, but they iterate through a series of increments, thus reducing the complexity of the task, and increasing the probability of learning from experience, won as each increment develops, and as the true cost of the increment becomes a fact.
'When the development and test of an increment are complete, an estimate to complete the remaining increments is computed.' (p. 474)
This article is far richer than our few selected quotations can show, with regard to concepts of cost estimation and control.

## Slide 44: Quinnan: IBM FSD Cleanroom Dynamic Design to Cost
Quinnan describes the process control loop used by IBM FSD to ensure that cost targets are met.
'Cost management. . . yields valid cost plans linked to technical performance. Our practice carries cost management farther by introducing design-to-cost guidance. Design, development, and managerial practices are applied in an integrated way to ensure that software technical management is consistent with cost management. The method [illustrated in this book by Figure 7.10] consists of developing a design, estimating its cost, and ensuring that the design is cost-effective.' (p. 473)
He goes on to describe a design iteration process trying to meet cost targets by either redesign or by sacrificing 'planned capability.' When a satisfactory design at cost target is achieved for a single increment, the 'development of each increment can proceed concurrently with the program design of the others.'
'Design is an iterative process in which each design level is a refinement of the previous level.' (p. 474)
It is clear from this that they avoid the big bang cost estimation approach. Not only do they iterate in seeking the appropriate balance between cost and design for a single increment, but they iterate through a series of increments, thus reducing the complexity of the task, and increasing the probability of learning from experience, won as each increment develops, and as the true cost of the increment becomes a fact.
'When the development and test of an increment are complete, an estimate to complete the remaining increments is computed.' (p. 474)
Source: Robert E. Quinnan, 'Software Engineering Management Practices', IBM Systems Journal, Vol. 19, No. 4, 1980, pp. 466~77
This text is cut from Gilb: The Principles of Software Engineering Management, 1988
but they iterate through a series of increments,
thus reducing the complexity of the task,
and increasing the probability of learning from experience
Notes: Slide developed Oct 6 2013 tsg for London Software Architecture Conference Talk 9 Oct 2013
15.1.18 Quinnan
Source: Robert E. Quinnan, 'Software Engineering Management Practices', IBM Systems Journal, Vol. 19, No. 4, 1980, pp. 466~77
Robert E. Quinnan: The Management of Software Engineering. Part V: Software Engineering Management Practices. IBM Systems Journal 19(4): 466-477 (1980)
Quinnan describes the process control loop used by IBM FSD to ensure that cost targets are met.
'Cost management. . . yields valid cost plans linked to technical performance. Our practice carries cost management farther by introducing design-to-cost guidance. Design, development, and managerial practices are applied in an integrated way to ensure that software technical management is consistent with cost management. The method [illustrated in this book by Figure 7.10] consists of developing a design, estimating its cost, and ensuring that the design is cost-effective.' (p. 473)
He goes on to describe a design iteration process trying to meet cost targets by either redesign or by sacrificing 'planned capability.' When a satisfactory design at cost target is achieved for a single increment, the 'development of each increment can proceed concurrently with the program design of the others.'
'Design is an iterative process in which each design level is a refinement of the previous level.' (p. 474)
It is clear from this that they avoid the big bang cost estimation approach. Not only do they iterate in seeking the appropriate balance between cost and design for a single increment, but they iterate through a series of increments, thus reducing the complexity of the task, and increasing the probability of learning from experience, won as each increment develops, and as the true cost of the increment becomes a fact.
'When the development and test of an increment are complete, an estimate to complete the remaining increments is computed.' (p. 474)
This article is far richer than our few selected quotations can show, with regard to concepts of cost estimation and control.

## Slide 45: Quinnan: IBM FSD Cleanroom Dynamic Design to Cost
Quinnan describes the process control loop used by IBM FSD to ensure that cost targets are met.
'Cost management. . . yields valid cost plans linked to technical performance. Our practice carries cost management farther by introducing design-to-cost guidance. Design, development, and managerial practices are applied in an integrated way to ensure that software technical management is consistent with cost management. The method [illustrated in this book by Figure 7.10] consists of developing a design, estimating its cost, and ensuring that the design is cost-effective.' (p. 473)
He goes on to describe a design iteration process trying to meet cost targets by either redesign or by sacrificing 'planned capability.' When a satisfactory design at cost target is achieved for a single increment, the 'development of each increment can proceed concurrently with the program design of the others.'
'Design is an iterative process in which each design level is a refinement of the previous level.' (p. 474)
It is clear from this that they avoid the big bang cost estimation approach. Not only do they iterate in seeking the appropriate balance between cost and design for a single increment, but they iterate through a series of increments, thus reducing the complexity of the task, and increasing the probability of learning from experience, won as each increment develops, and as the true cost of the increment becomes a fact.
'When the development and test of an increment are complete, an estimate to complete the remaining increments is computed.' (p. 474)
Source: Robert E. Quinnan, 'Software Engineering Management Practices', IBM Systems Journal, Vol. 19, No. 4, 1980, pp. 466~77
This text is cut from Gilb: The Principles of Software Engineering Management, 1988
an estimate to complete the remaining increments is computed.
Notes: Slide developed Oct 6 2013 tsg for London Software Architecture Conference Talk 9 Oct 2013
15.1.18 Quinnan
Source: Robert E. Quinnan, 'Software Engineering Management Practices', IBM Systems Journal, Vol. 19, No. 4, 1980, pp. 466~77
Robert E. Quinnan: The Management of Software Engineering. Part V: Software Engineering Management Practices. IBM Systems Journal 19(4): 466-477 (1980)
Quinnan describes the process control loop used by IBM FSD to ensure that cost targets are met.
'Cost management. . . yields valid cost plans linked to technical performance. Our practice carries cost management farther by introducing design-to-cost guidance. Design, development, and managerial practices are applied in an integrated way to ensure that software technical management is consistent with cost management. The method [illustrated in this book by Figure 7.10] consists of developing a design, estimating its cost, and ensuring that the design is cost-effective.' (p. 473)
He goes on to describe a design iteration process trying to meet cost targets by either redesign or by sacrificing 'planned capability.' When a satisfactory design at cost target is achieved for a single increment, the 'development of each increment can proceed concurrently with the program design of the others.'
'Design is an iterative process in which each design level is a refinement of the previous level.' (p. 474)
It is clear from this that they avoid the big bang cost estimation approach. Not only do they iterate in seeking the appropriate balance between cost and design for a single increment, but they iterate through a series of increments, thus reducing the complexity of the task, and increasing the probability of learning from experience, won as each increment develops, and as the true cost of the increment becomes a fact.
'When the development and test of an increment are complete, an estimate to complete the remaining increments is computed.' (p. 474)
This article is far richer than our few selected quotations can show, with regard to concepts of cost estimation and control.

## Slide 46: Principle 8. Change requirements, based on quantified experience, new inputs: intelligent tradeoff.
Reduce the level or delivery time, of lower-priority requirements,
in order to deliver high priority requirements
on time,
within budget, or at Goal levels.
Notes: http://projects.staffs.ac.uk/suniwe/images/rup-cycle.gif

## Slide 47: REAL EXAMPLE: Cleanroom Method, developed by IBM’s Harlan Mills (1970-80) EARLY AGILE !!!
“Software Engineering began to emerge in FSD” (IBM Federal Systems Division, from 1996 a part of Lockheed Martin Marietta) “some ten years ago [Ed. about 1970] in a continuing evolution that is still underway:
Ten years ago general management expected the worst from software projects – cost overruns, late deliveries, unreliable and incomplete software
Today [Ed. 1980!], management has learned to expect on-time, within budget, deliveries of high-quality software. A Navy helicopter ship system, called LAMPS, provides a recent example. LAMPS software was a four-year project of over 200 person-years of effort, developing over three million, and integrating over seven million words of program and data for eight different processors distributed between a helicopter and a ship in 45 incremental deliveries [Ed. Note 2%!]s. Every one of those deliveries was on time and under budget
A more extended example can be found in the NASA space program,
- Where in the past ten years, FSD has managed some 7,000 person-years of software development, developing and integrating over a hundred million bytes of program and data for ground and space processors in over a dozen projects.
- There were few late or overrun deliveries in that decade, and none at all in the past four years.”
Notes: A time or cost estimate, once it becomes a deadline or a budget respectively, is a ‘limited resource’. One of the smartest ways to deal with limited resources is intelligent prioritization (Gilb and Maier 2005). Instead of implementing all your designs in a ‘big bang’ manner, and hoping to meet all the requirements and resource (time and cost) estimates, we suggest you deliver the project value a little bit at a time, and see how each of the designs actually works, and what they each actually cost. ‘A little bit at a time’ should be interpreted as delivering evolutionary steps of approximately 2% of the overall project timescales (say weekly, fortnightly or monthly cycles), and hopefully about 2% of the project financial budget.
Planguage’s impact estimation (IE) method (Gilb 1988; Gilb 2005) is helpful in identifying the designs that give the estimated best stakeholder value for their costs. We implement designs incrementally so that we can get acceptable feedback on costs, and value delivery (in terms of meeting requirements). With a bit of luck, stakeholders then receive interesting value very early, and what works and what doesn’t is learned in practice. If a deadline is hit, or if the budget runs out (possibly because of a deadline being moved up earlier or a budget cut!), then at least there is still a complete live real system with delivered high-value. In such situations, the whole concept of the project-level estimates, the deadlines and the budgets is not so important any more.
Nobody does it better! Harlan Mills told me that they had to solve the persistent problem of cost overruns, in relation to the contracted estimates, because the government was getting smarter, and using fixed-price contracts (as opposed to cost plus). If the project ran over, IBM lost its own profit. If IBM did not find a better way, they could just as well leave the business (Personal Communication).
Notice the “45 deliveries” Mills cites. That means 2% delivery cycles. IBM was using intelligent feedback and learning. They actually had very sophisticated estimation technology based on a thorough collection of experiences (Walston and Felix 1977). But this did not give them the accuracy they needed to avoid losing money. Lets us say they had a 40% profit margin, and they could be wrong by 40% to 200% (The NASA range, see earlier Figure 3). They would still lose money on most contracts. So, they had to compensate for their estimation inaccuracy by incremental feedback, and necessary change, to come in ‘on time and under budget every time’. Mills’ colleague, Quinnan describes their process of intelligent dynamic prioritization in detail in (Mills 1980 in IBM SJ 4-1980).
A thorough explanation of systems development processes helping achieve intelligent prioritization is found in (Gilb 2005). See also Figure 9. Nothing less will suffice for large and complex systems (that is, for project involving hundreds of staff, years of effort, and sometimes $100 million or more in cost). For smaller systems (small teams over a few months), several organizations have made good simple practical adaptations (Upadhyayula 2001 (Study of Evo at HP in 1990s); Johansen and Gilb 2005) of the essential ‘Evo’ development process ideas (Evo itself predating later ‘Agile’ methods)[Denning 2010, p.129] & [Gilb 2010c].
The agile community has adopted small iterative cycles (Gilb 2010c), but they have failed to adopt the notion of measurement of value and quality – which is essential for larger projects, and some smaller ones. Without explicit absolute quality requirement and design impact metrics, the value prioritization is ambiguous and too subjective (Gilb 2010c; Gilb and Brodie 2010).

## Slide 48: In the Cleanroom Method, developed by IBM’s Harlan Mills (1980) they reported note: real Agile large scale from 1970-80!
“Software Engineering began to emerge in FSD” (IBM Federal Systems Division, from 1996 a part of Lockheed Martin Marietta) “some ten years ago [Ed. about 1970] in a continuing evolution that is still underway:
Ten years ago general management expected the worst from software projects – cost overruns, late deliveries, unreliable and incomplete software
Today [Ed. 1980!], management has learned to expect on-time, within budget, deliveries of high-quality software. A Navy helicopter ship system, called LAMPS, provides a recent example. LAMPS software was a four-year project of over 200 person-years of effort, developing over three million, and integrating over seven million words of program and data for eight different processors distributed between a helicopter and a ship in 45 incremental deliveries [Ed. Note 2%!]s. Every one of those deliveries was on time and under budget
A more extended example can be found in the NASA space program,
- Where in the past ten years, FSD has managed some 7,000 person-years of software development, developing and integrating over a hundred million bytes of program and data for ground and space processors in over a dozen projects.
- There were few late or overrun deliveries in that decade, and none at all in the past four years.”
in 45 incremental deliveries
were few late or overrun deliveries in that decade, and none at all in the past four years
Notes: A time or cost estimate, once it becomes a deadline or a budget respectively, is a ‘limited resource’. One of the smartest ways to deal with limited resources is intelligent prioritization (Gilb and Maier 2005). Instead of implementing all your designs in a ‘big bang’ manner, and hoping to meet all the requirements and resource (time and cost) estimates, we suggest you deliver the project value a little bit at a time, and see how each of the designs actually works, and what they each actually cost. ‘A little bit at a time’ should be interpreted as delivering evolutionary steps of approximately 2% of the overall project timescales (say weekly, fortnightly or monthly cycles), and hopefully about 2% of the project financial budget.
Planguage’s impact estimation (IE) method (Gilb 1988; Gilb 2005) is helpful in identifying the designs that give the estimated best stakeholder value for their costs. We implement designs incrementally so that we can get acceptable feedback on costs, and value delivery (in terms of meeting requirements). With a bit of luck, stakeholders then receive interesting value very early, and what works and what doesn’t is learned in practice. If a deadline is hit, or if the budget runs out (possibly because of a deadline being moved up earlier or a budget cut!), then at least there is still a complete live real system with delivered high-value. In such situations, the whole concept of the project-level estimates, the deadlines and the budgets is not so important any more.
Nobody does it better! Harlan Mills told me that they had to solve the persistent problem of cost overruns, in relation to the contracted estimates, because the government was getting smarter, and using fixed-price contracts (as opposed to cost plus). If the project ran over, IBM lost its own profit. If IBM did not find a better way, they could just as well leave the business (Personal Communication).
Notice the “45 deliveries” Mills cites. That means 2% delivery cycles. IBM was using intelligent feedback and learning. They actually had very sophisticated estimation technology based on a thorough collection of experiences (Walston and Felix 1977). But this did not give them the accuracy they needed to avoid losing money. Lets us say they had a 40% profit margin, and they could be wrong by 40% to 200% (The NASA range, see earlier Figure 3). They would still lose money on most contracts. So, they had to compensate for their estimation inaccuracy by incremental feedback, and necessary change, to come in ‘on time and under budget every time’. Mills’ colleague, Quinnan describes their process of intelligent dynamic prioritization in detail in (Mills 1980 in IBM SJ 4-1980).
A thorough explanation of systems development processes helping achieve intelligent prioritization is found in (Gilb 2005). See also Figure 9. Nothing less will suffice for large and complex systems (that is, for project involving hundreds of staff, years of effort, and sometimes $100 million or more in cost). For smaller systems (small teams over a few months), several organizations have made good simple practical adaptations (Upadhyayula 2001 (Study of Evo at HP in 1990s); Johansen and Gilb 2005) of the essential ‘Evo’ development process ideas (Evo itself predating later ‘Agile’ methods)[Denning 2010, p.129] & [Gilb 2010c].
The agile community has adopted small iterative cycles (Gilb 2010c), but they have failed to adopt the notion of measurement of value and quality – which is essential for larger projects, and some smaller ones. Without explicit absolute quality requirement and design impact metrics, the value prioritization is ambiguous and too subjective (Gilb 2010c; Gilb and Brodie 2010).

## Slide 49: Quinnan: IBM FSD Cleanroom Dynamic Design to Cost
Quinnan describes the process control loop used by IBM FSD to ensure that cost targets are met.
'Cost management. . . yields valid cost plans linked to technical performance. Our practice carries cost management farther by introducing design-to-cost guidance. Design, development, and managerial practices are applied in an integrated way to ensure that software technical management is consistent with cost management. The method [illustrated in this book by Figure 7.10] consists of developing a design, estimating its cost, and ensuring that the design is cost-effective.' (p. 473)
He goes on to describe a design iteration process trying to meet cost targets by either redesign or by sacrificing 'planned capability.' When a satisfactory design at cost target is achieved for a single increment, the 'development of each increment can proceed concurrently with the program design of the others.'
'Design is an iterative process in which each design level is a refinement of the previous level.' (p. 474)
It is clear from this that they avoid the big bang cost estimation approach. Not only do they iterate in seeking the appropriate balance between cost and design for a single increment, but they iterate through a series of increments, thus reducing the complexity of the task, and increasing the probability of learning from experience, won as each increment develops, and as the true cost of the increment becomes a fact.
'When the development and test of an increment are complete, an estimate to complete the remaining increments is computed.' (p. 474)
Source: Robert E. Quinnan, 'Software Engineering Management Practices', IBM Systems Journal, Vol. 19, No. 4, 1980, pp. 466~77
This text is cut from Gilb: The Principles of Software Engineering Management, 1988
Notes: Slide developed Oct 6 2013 tsg for London Software Architecture Conference Talk 9 Oct 2013
15.1.18 Quinnan
Source: Robert E. Quinnan, 'Software Engineering Management Practices', IBM Systems Journal, Vol. 19, No. 4, 1980, pp. 466~77
Robert E. Quinnan: The Management of Software Engineering. Part V: Software Engineering Management Practices. IBM Systems Journal 19(4): 466-477 (1980)
Quinnan describes the process control loop used by IBM FSD to ensure that cost targets are met.
'Cost management. . . yields valid cost plans linked to technical performance. Our practice carries cost management farther by introducing design-to-cost guidance. Design, development, and managerial practices are applied in an integrated way to ensure that software technical management is consistent with cost management. The method [illustrated in this book by Figure 7.10] consists of developing a design, estimating its cost, and ensuring that the design is cost-effective.' (p. 473)
He goes on to describe a design iteration process trying to meet cost targets by either redesign or by sacrificing 'planned capability.' When a satisfactory design at cost target is achieved for a single increment, the 'development of each increment can proceed concurrently with the program design of the others.'
'Design is an iterative process in which each design level is a refinement of the previous level.' (p. 474)
It is clear from this that they avoid the big bang cost estimation approach. Not only do they iterate in seeking the appropriate balance between cost and design for a single increment, but they iterate through a series of increments, thus reducing the complexity of the task, and increasing the probability of learning from experience, won as each increment develops, and as the true cost of the increment becomes a fact.
'When the development and test of an increment are complete, an estimate to complete the remaining increments is computed.' (p. 474)
This article is far richer than our few selected quotations can show, with regard to concepts of cost estimation and control.

## Slide 50: Quinnan: IBM FSD Cleanroom Dynamic Design to Cost
Quinnan describes the process control loop used by IBM FSD to ensure that cost targets are met.
'Cost management. . . yields valid cost plans linked to technical performance. Our practice carries cost management farther by introducing design-to-cost guidance. Design, development, and managerial practices are applied in an integrated way to ensure that software technical management is consistent with cost management. The method [illustrated in this book by Figure 7.10] consists of developing a design, estimating its cost, and ensuring that the design is cost-effective.' (p. 473)
He goes on to describe a design iteration process trying to meet cost targets by either redesign or by sacrificing 'planned capability.' When a satisfactory design at cost target is achieved for a single increment, the 'development of each increment can proceed concurrently with the program design of the others.'
'Design is an iterative process in which each design level is a refinement of the previous level.' (p. 474)
It is clear from this that they avoid the big bang cost estimation approach. Not only do they iterate in seeking the appropriate balance between cost and design for a single increment, but they iterate through a series of increments, thus reducing the complexity of the task, and increasing the probability of learning from experience, won as each increment develops, and as the true cost of the increment becomes a fact.
'When the development and test of an increment are complete, an estimate to complete the remaining increments is computed.' (p. 474)
Source: Robert E. Quinnan, 'Software Engineering Management Practices', IBM Systems Journal, Vol. 19, No. 4, 1980, pp. 466~77
This text is cut from Gilb: The Principles of Software Engineering Management, 1988
of developing a design, estimating its cost, and ensuring that the design is cost-effective
Notes: Slide developed Oct 6 2013 tsg for London Software Architecture Conference Talk 9 Oct 2013
15.1.18 Quinnan
Source: Robert E. Quinnan, 'Software Engineering Management Practices', IBM Systems Journal, Vol. 19, No. 4, 1980, pp. 466~77
Robert E. Quinnan: The Management of Software Engineering. Part V: Software Engineering Management Practices. IBM Systems Journal 19(4): 466-477 (1980)
Quinnan describes the process control loop used by IBM FSD to ensure that cost targets are met.
'Cost management. . . yields valid cost plans linked to technical performance. Our practice carries cost management farther by introducing design-to-cost guidance. Design, development, and managerial practices are applied in an integrated way to ensure that software technical management is consistent with cost management. The method [illustrated in this book by Figure 7.10] consists of developing a design, estimating its cost, and ensuring that the design is cost-effective.' (p. 473)
He goes on to describe a design iteration process trying to meet cost targets by either redesign or by sacrificing 'planned capability.' When a satisfactory design at cost target is achieved for a single increment, the 'development of each increment can proceed concurrently with the program design of the others.'
'Design is an iterative process in which each design level is a refinement of the previous level.' (p. 474)
It is clear from this that they avoid the big bang cost estimation approach. Not only do they iterate in seeking the appropriate balance between cost and design for a single increment, but they iterate through a series of increments, thus reducing the complexity of the task, and increasing the probability of learning from experience, won as each increment develops, and as the true cost of the increment becomes a fact.
'When the development and test of an increment are complete, an estimate to complete the remaining increments is computed.' (p. 474)
This article is far richer than our few selected quotations can show, with regard to concepts of cost estimation and control.

## Slide 51: Quinnan: IBM FSD Cleanroom Dynamic Design to Cost
Quinnan describes the process control loop used by IBM FSD to ensure that cost targets are met.
'Cost management. . . yields valid cost plans linked to technical performance. Our practice carries cost management farther by introducing design-to-cost guidance. Design, development, and managerial practices are applied in an integrated way to ensure that software technical management is consistent with cost management. The method [illustrated in this book by Figure 7.10] consists of developing a design, estimating its cost, and ensuring that the design is cost-effective.' (p. 473)
He goes on to describe a design iteration process trying to meet cost targets by either redesign or by sacrificing 'planned capability.' When a satisfactory design at cost target is achieved for a single increment, the 'development of each increment can proceed concurrently with the program design of the others.'
'Design is an iterative process in which each design level is a refinement of the previous level.' (p. 474)
It is clear from this that they avoid the big bang cost estimation approach. Not only do they iterate in seeking the appropriate balance between cost and design for a single increment, but they iterate through a series of increments, thus reducing the complexity of the task, and increasing the probability of learning from experience, won as each increment develops, and as the true cost of the increment becomes a fact.
'When the development and test of an increment are complete, an estimate to complete the remaining increments is computed.' (p. 474)
Source: Robert E. Quinnan, 'Software Engineering Management Practices', IBM Systems Journal, Vol. 19, No. 4, 1980, pp. 466~77
This text is cut from Gilb: The Principles of Software Engineering Management, 1988
iteration process trying to meet cost targets by either redesign or by sacrificing 'planned capability’
Notes: Slide developed Oct 6 2013 tsg for London Software Architecture Conference Talk 9 Oct 2013
15.1.18 Quinnan
Source: Robert E. Quinnan, 'Software Engineering Management Practices', IBM Systems Journal, Vol. 19, No. 4, 1980, pp. 466~77
Robert E. Quinnan: The Management of Software Engineering. Part V: Software Engineering Management Practices. IBM Systems Journal 19(4): 466-477 (1980)
Quinnan describes the process control loop used by IBM FSD to ensure that cost targets are met.
'Cost management. . . yields valid cost plans linked to technical performance. Our practice carries cost management farther by introducing design-to-cost guidance. Design, development, and managerial practices are applied in an integrated way to ensure that software technical management is consistent with cost management. The method [illustrated in this book by Figure 7.10] consists of developing a design, estimating its cost, and ensuring that the design is cost-effective.' (p. 473)
He goes on to describe a design iteration process trying to meet cost targets by either redesign or by sacrificing 'planned capability.' When a satisfactory design at cost target is achieved for a single increment, the 'development of each increment can proceed concurrently with the program design of the others.'
'Design is an iterative process in which each design level is a refinement of the previous level.' (p. 474)
It is clear from this that they avoid the big bang cost estimation approach. Not only do they iterate in seeking the appropriate balance between cost and design for a single increment, but they iterate through a series of increments, thus reducing the complexity of the task, and increasing the probability of learning from experience, won as each increment develops, and as the true cost of the increment becomes a fact.
'When the development and test of an increment are complete, an estimate to complete the remaining increments is computed.' (p. 474)
This article is far richer than our few selected quotations can show, with regard to concepts of cost estimation and control.

## Slide 52: Quinnan: IBM FSD Cleanroom Dynamic Design to Cost
Quinnan describes the process control loop used by IBM FSD to ensure that cost targets are met.
'Cost management. . . yields valid cost plans linked to technical performance. Our practice carries cost management farther by introducing design-to-cost guidance. Design, development, and managerial practices are applied in an integrated way to ensure that software technical management is consistent with cost management. The method [illustrated in this book by Figure 7.10] consists of developing a design, estimating its cost, and ensuring that the design is cost-effective.' (p. 473)
He goes on to describe a design iteration process trying to meet cost targets by either redesign or by sacrificing 'planned capability.' When a satisfactory design at cost target is achieved for a single increment, the 'development of each increment can proceed concurrently with the program design of the others.'
'Design is an iterative process in which each design level is a refinement of the previous level.' (p. 474)
It is clear from this that they avoid the big bang cost estimation approach. Not only do they iterate in seeking the appropriate balance between cost and design for a single increment, but they iterate through a series of increments, thus reducing the complexity of the task, and increasing the probability of learning from experience, won as each increment develops, and as the true cost of the increment becomes a fact.
'When the development and test of an increment are complete, an estimate to complete the remaining increments is computed.' (p. 474)
Source: Robert E. Quinnan, 'Software Engineering Management Practices', IBM Systems Journal, Vol. 19, No. 4, 1980, pp. 466~77
This text is cut from Gilb: The Principles of Software Engineering Management, 1988
Design is an iterative process
Notes: Slide developed Oct 6 2013 tsg for London Software Architecture Conference Talk 9 Oct 2013
15.1.18 Quinnan
Source: Robert E. Quinnan, 'Software Engineering Management Practices', IBM Systems Journal, Vol. 19, No. 4, 1980, pp. 466~77
Robert E. Quinnan: The Management of Software Engineering. Part V: Software Engineering Management Practices. IBM Systems Journal 19(4): 466-477 (1980)
Quinnan describes the process control loop used by IBM FSD to ensure that cost targets are met.
'Cost management. . . yields valid cost plans linked to technical performance. Our practice carries cost management farther by introducing design-to-cost guidance. Design, development, and managerial practices are applied in an integrated way to ensure that software technical management is consistent with cost management. The method [illustrated in this book by Figure 7.10] consists of developing a design, estimating its cost, and ensuring that the design is cost-effective.' (p. 473)
He goes on to describe a design iteration process trying to meet cost targets by either redesign or by sacrificing 'planned capability.' When a satisfactory design at cost target is achieved for a single increment, the 'development of each increment can proceed concurrently with the program design of the others.'
'Design is an iterative process in which each design level is a refinement of the previous level.' (p. 474)
It is clear from this that they avoid the big bang cost estimation approach. Not only do they iterate in seeking the appropriate balance between cost and design for a single increment, but they iterate through a series of increments, thus reducing the complexity of the task, and increasing the probability of learning from experience, won as each increment develops, and as the true cost of the increment becomes a fact.
'When the development and test of an increment are complete, an estimate to complete the remaining increments is computed.' (p. 474)
This article is far richer than our few selected quotations can show, with regard to concepts of cost estimation and control.

## Slide 53: Quinnan: IBM FSD Cleanroom Dynamic Design to Cost
Quinnan describes the process control loop used by IBM FSD to ensure that cost targets are met.
'Cost management. . . yields valid cost plans linked to technical performance. Our practice carries cost management farther by introducing design-to-cost guidance. Design, development, and managerial practices are applied in an integrated way to ensure that software technical management is consistent with cost management. The method [illustrated in this book by Figure 7.10] consists of developing a design, estimating its cost, and ensuring that the design is cost-effective.' (p. 473)
He goes on to describe a design iteration process trying to meet cost targets by either redesign or by sacrificing 'planned capability.' When a satisfactory design at cost target is achieved for a single increment, the 'development of each increment can proceed concurrently with the program design of the others.'
'Design is an iterative process in which each design level is a refinement of the previous level.' (p. 474)
It is clear from this that they avoid the big bang cost estimation approach. Not only do they iterate in seeking the appropriate balance between cost and design for a single increment, but they iterate through a series of increments, thus reducing the complexity of the task, and increasing the probability of learning from experience, won as each increment develops, and as the true cost of the increment becomes a fact.
'When the development and test of an increment are complete, an estimate to complete the remaining increments is computed.' (p. 474)
Source: Robert E. Quinnan, 'Software Engineering Management Practices', IBM Systems Journal, Vol. 19, No. 4, 1980, pp. 466~77
This text is cut from Gilb: The Principles of Software Engineering Management, 1988
but they iterate through a series of increments,
thus reducing the complexity of the task,
and increasing the probability of learning from experience
Notes: Slide developed Oct 6 2013 tsg for London Software Architecture Conference Talk 9 Oct 2013
15.1.18 Quinnan
Source: Robert E. Quinnan, 'Software Engineering Management Practices', IBM Systems Journal, Vol. 19, No. 4, 1980, pp. 466~77
Robert E. Quinnan: The Management of Software Engineering. Part V: Software Engineering Management Practices. IBM Systems Journal 19(4): 466-477 (1980)
Quinnan describes the process control loop used by IBM FSD to ensure that cost targets are met.
'Cost management. . . yields valid cost plans linked to technical performance. Our practice carries cost management farther by introducing design-to-cost guidance. Design, development, and managerial practices are applied in an integrated way to ensure that software technical management is consistent with cost management. The method [illustrated in this book by Figure 7.10] consists of developing a design, estimating its cost, and ensuring that the design is cost-effective.' (p. 473)
He goes on to describe a design iteration process trying to meet cost targets by either redesign or by sacrificing 'planned capability.' When a satisfactory design at cost target is achieved for a single increment, the 'development of each increment can proceed concurrently with the program design of the others.'
'Design is an iterative process in which each design level is a refinement of the previous level.' (p. 474)
It is clear from this that they avoid the big bang cost estimation approach. Not only do they iterate in seeking the appropriate balance between cost and design for a single increment, but they iterate through a series of increments, thus reducing the complexity of the task, and increasing the probability of learning from experience, won as each increment develops, and as the true cost of the increment becomes a fact.
'When the development and test of an increment are complete, an estimate to complete the remaining increments is computed.' (p. 474)
This article is far richer than our few selected quotations can show, with regard to concepts of cost estimation and control.

## Slide 54: Quinnan: IBM FSD Cleanroom Dynamic Design to Cost
Quinnan describes the process control loop used by IBM FSD to ensure that cost targets are met.
'Cost management. . . yields valid cost plans linked to technical performance. Our practice carries cost management farther by introducing design-to-cost guidance. Design, development, and managerial practices are applied in an integrated way to ensure that software technical management is consistent with cost management. The method [illustrated in this book by Figure 7.10] consists of developing a design, estimating its cost, and ensuring that the design is cost-effective.' (p. 473)
He goes on to describe a design iteration process trying to meet cost targets by either redesign or by sacrificing 'planned capability.' When a satisfactory design at cost target is achieved for a single increment, the 'development of each increment can proceed concurrently with the program design of the others.'
'Design is an iterative process in which each design level is a refinement of the previous level.' (p. 474)
It is clear from this that they avoid the big bang cost estimation approach. Not only do they iterate in seeking the appropriate balance between cost and design for a single increment, but they iterate through a series of increments, thus reducing the complexity of the task, and increasing the probability of learning from experience, won as each increment develops, and as the true cost of the increment becomes a fact.
'When the development and test of an increment are complete, an estimate to complete the remaining increments is computed.' (p. 474)
Source: Robert E. Quinnan, 'Software Engineering Management Practices', IBM Systems Journal, Vol. 19, No. 4, 1980, pp. 466~77
This text is cut from Gilb: The Principles of Software Engineering Management, 1988
an estimate to complete the remaining increments is computed.
Notes: Slide developed Oct 6 2013 tsg for London Software Architecture Conference Talk 9 Oct 2013
15.1.18 Quinnan
Source: Robert E. Quinnan, 'Software Engineering Management Practices', IBM Systems Journal, Vol. 19, No. 4, 1980, pp. 466~77
Robert E. Quinnan: The Management of Software Engineering. Part V: Software Engineering Management Practices. IBM Systems Journal 19(4): 466-477 (1980)
Quinnan describes the process control loop used by IBM FSD to ensure that cost targets are met.
'Cost management. . . yields valid cost plans linked to technical performance. Our practice carries cost management farther by introducing design-to-cost guidance. Design, development, and managerial practices are applied in an integrated way to ensure that software technical management is consistent with cost management. The method [illustrated in this book by Figure 7.10] consists of developing a design, estimating its cost, and ensuring that the design is cost-effective.' (p. 473)
He goes on to describe a design iteration process trying to meet cost targets by either redesign or by sacrificing 'planned capability.' When a satisfactory design at cost target is achieved for a single increment, the 'development of each increment can proceed concurrently with the program design of the others.'
'Design is an iterative process in which each design level is a refinement of the previous level.' (p. 474)
It is clear from this that they avoid the big bang cost estimation approach. Not only do they iterate in seeking the appropriate balance between cost and design for a single increment, but they iterate through a series of increments, thus reducing the complexity of the task, and increasing the probability of learning from experience, won as each increment develops, and as the true cost of the increment becomes a fact.
'When the development and test of an increment are complete, an estimate to complete the remaining increments is computed.' (p. 474)
This article is far richer than our few selected quotations can show, with regard to concepts of cost estimation and control.

## Slide 55: Principle 9. Involve the stakeholders, every week, in setting quantified goals
It is much easier to determine requirements with a little hindsight!
The eternal cycle of stakeholder priorities
Notes: http://www.performance-measurement.net/assets/neely/prism03.gif
It is much easier to determine requirements with a little hindsight!
(I just invented this now as I was making the slide June 8 2010 Tom Gilb)

## Slide 56: Concurrent Quantified ‘Empowered Creativity’ * The Software Engineers can use ANY design that they believe delivers the planned value. And keep what really works
Confirmit Product
Team 2
Team 3
Team 4
Team 1
* Empowered Creativity: Term coined by Trond Johansen, Confirmit, 2003
Notes: Originated March 12 2013 Stockholm tsg

## Slide 57: EVO Plan Confirmit 8.5 in Evo Step Impact Measurement 4 product areas were attacked in all: 25 Qualities concurrently, one quarter of a year. Total development staff = 13
9
8
3
3

## Slide 58: Evo’s impact on Confirmit product qualities 1st Qtr
Only 5 highlights of the 25 impacts are listed here
Release 8.5

## Slide 59: 10. Involve the stakeholders, every week, in actually using increments
Notes: http://www.lab49.com/files/company/IterativeProjectDelivery.png

## Slide 60: Quantified Value Delivery Project Management in a Nutshell Quantified Value Requirements, Design, Design Value/cost estimation, Measurement of Value Delivery, Incremental Project Progress to Date
Cumulative
weekly
progress
metric
Priority
Next week
Warning
metrics based
Constraint
Target
Estimates
Weekly
Testing

## Slide 61: EVO Plan Confirmit 8.5 in Evo Step Impact Measurement 4 product areas were attacked in all: 25 Qualities concurrently, one quarter of a year. Total development staff = 13
9
8
3
3

## Slide 62: Code quality – ”green” week, 2005 “Refactoring by Proactive Design Engineering!”
In these ”green” weeks, some of the deliverables will be less visible for the end users, but more visible for our QA department.
We manage code quality through an Impact Estimation table.
Speed
Maintainability
Nunit Tests
PeerTests
TestDirectorTests
Robustness.Correctness
Robustness.Boundary Conditions
ResourceUsage.CPU
Maintainability.DocCode
SynchronizationStatus
Notes: I think he said these were every 4th or 5th week, TG May 7 2005

## Slide 63: Raising the Levels of Maintainability like ‘Mean Time To Fix a Bug’
Current
Level
Minimum Future Level
Competitive and economic Goal level
Notes: Slide originated 3 Nov 2013 for Smidig 2013 Oslo TsG

## Slide 64: Raising the Levels of Maintainability Multiple Attributes of Technical Debt
Portability
Scalability
Adaptability
Testability
Notes: Slide originated 3 Nov 2013 for Smidig 2013 Oslo TsG

## Slide 65: Broader ‘Maintainability’ Concepts ALL quantified, with a defined Scale of measure in CE-5
Notes: Source Competitive Engineering book, Glossary, Requirement

## Slide 66: 1. The Conscious Design Principle:
“Maintainability must be consciously designed into a system:
  failure to design to a set of levels of maintainability
  means the resulting maintainability is both bad and random. ”
  © Tom Gilb (2008, INCOSE Paper)
    http://www.gilb.com/tiki-download_file.php?fileId=138
Notes: Source of This principles
Gilb ACCU Designing Maintainability Friday 1400 90 minutes.ppt (10.41 Mb)
You can download this file using: http://www.gilb.com/tiki-download_file.php?fileId=171
Maintainability Paper
http://www.gilb.com/tiki-download_file.php?fileId=138
Designing Maintainability in Software Engineering: a Quantified Approach.
Tom Gilb Result Planning Limited Tom.Gilb@INCOSE.org
Copyright © 2008 by Tom Gilb. Published and used by INCOSE with permission.
Principles of Software Maintainability
I would like to suggest a set of principles about software maintainability, in order to give this paper a framework:
1. The Conscious Design Principle: Maintainability must be consciously designed into a system: failure to design to a set of levels of maintainability means the resulting maintainability is both bad and random.
2. The Many-Splendored Thing Principle. Maintainability is a wide set of change quality types, under a wide variety of circumstances: so we must clearly define what we are trying to engineer.
3. The Multi-Level Requirement Principle. The levels of maintainability we decide to require are partly constraints, a necessary minimum of ability to avoid failure, and partly desirable target levels that are determined by what pays off to invest in.
4. The Payoff Level Principle. The levels of maintainability it pays off to invest in, depend on many factors – but certainly on the system lifetime expectancy, the criticality/illegality/cost of not being able to change correctly or change in time, and the cost and availability of necessary skilled professionals to carry out the changes.
5. The Priority Dynamics Principle. The maintainability requirements must compete for priority for limited resources with all other requirements. We cannot simply demand arbitrary desired levels of maintainability.
http://www.learntarot.com/bigjpgs/maj01.jpg
The Magician is the archetype of the active, masculine principle - the ultimate achiever. He symbolizes the power to tap universal forces and use them for creative purposes. Note his stance in the picture. He acts as a lightening rod - one arm extended up into the Divine for inspiration, the other pointing toward Earth to ground this potent energy. [note] His abilities appear magical at times because his will helps him achieve what seem to be miracles.What makes the Magician so powerful? First, he is not afraid to act. He believes in himself and is willing to put that belief on the line. He also knows what he intends to do and why. He doesn't hesitate because he understands his situation exactly. The Magician can focus with single-minded determination. As long as he remembers the divine source of his power, the Magician remains the perfect conduit for miracles.In a reading, the Magician implies that the primal forces of creativity are yours if you can claim your power and act with awareness and concentration. This card is a signal to act and act now, provided you understand exactly what you want and are committed to getting it.
http://learntarot.org/maj01.htm
taking actiondoing what needs to be donerealizing your potentialmaking what's possible realpracticing what you preachcarrying out plansproducing magical resultsusing your talentsacting consciouslyknowing what you are doing and whyacknowledging your motivationsunderstanding your intentionsexamining the known situationconcentratinghaving singleness of purposebeing totally committedapplying the force of your willfeeling centeredsetting aside distractionsfocusing on a goalexperiencing powermaking a strong impacthaving vitalitycreating miraclesbecoming energizedfeeling vigorousbeing creative

## Slide 67: The ‘Maintainability’ Generic Breakdown into Sub-problems
1. Problem Recognition Time.
How can we reduce the time from bug actually occurs until it is recognized and reported?
2. Administrative Delay Time:
How can we reduce the time from bug reported, until someone begins action on it?
3. Tool Collection Time.
How can we reduce the time delay to collect correct, complete and updated information to analyze the bug: source code, changes, database access, reports, similar reports, test cases, test outputs.
4. Problem Analysis Time.
Etc. for all the following phases defined, and implied, in the Scale scope above.
5. Correction Hypothesis Time
6. Quality Control Time
7. Change Time
8. Local Test Time
9. Field Pilot Test Time
10. Change Distribution Time
11. Customer Installation Time
12. Customer Damage Analysis Time
13. Customer Level Recovery Time
14. Customer QC of Recovery Time
Source: Competitive Engineering Ch 5
& Ireson (ed.) Reliability Handbook, 1966

## Slide 68: An Example of Specifying 1 Attribute in ‘Planguage’
Restore Speed:
Type: Software Quality Requirement. Version: 25 October 2007.
Part of: Rock Solid Robustness
Ambition: Should an error occur (or the user otherwise desire to do so), the system shall be able to restore the system to a previously saved state in less than 10 minutes. <-6.1.2 HFA.
Scale: Duration from Initiation of Restore to Complete and verified state of a defined [Previous: Default = Immediately Previous]] saved state.
Initiation: defined as {Operator Initiation, System Initiation, ?}. Default = Any.
Goal [ Initial and all subsequent released and Evo steps] 1 minute?
Fail [ Initial and all subsequent released and Evo steps] 10 minutes. <- 6.1.2 HFA
Catastrophe: 100 minutes.
Notes: Example 1c: The ‘Ambition’ level statement is a high lev el, not too quantitatively rigorous, summary of the requirement level we want. It is a healthy agreed prelude to more-rigorous definition. We often use the statements made poorly by management, and cite them as the source or authority. We then process with Scale and Goal etc. to define in an engineering manner.

## Slide 69: Let’s Vote
1. How many of you would prefer to keep doing conventional ‘softcrafter’ refactoring; even if the results were not measurable
2. How many of you think you ought to try to engineer measurable software maintainability results into your systems
  Even if your boss is not smart enough to ask you, or support you doing it?

## Slide 70: Further Reading: AgileRecord.com

## Slide 71: My 10 Agile Values?
Simplicity
  1. Focus on real stakeholder values
Communication
  2. Communicate stakeholder values quantitatively
  3. Estimate expected results and costs for weekly steps
Feedback
  4. Generate results, weekly, for stakeholders, in their environment
  5. Measure all critical aspects of the improved results cycle.
  6. Analyze deviation from your initial estimates
Courage
  7. Change plans to reflect weekly learning
  8. Immediately implement valued stakeholder needs, next week
    Don’t wait, don’t study (analysis paralysis), don’t make excuses.
    Just Do It!
  9. Tell stakeholders exactly what you will deliver next week
  10. Use any design, strategy, method, process that works quantitatively well - to get your results
    Be a systems engineer, not a just programmer (a ‘Softcrafter’).
    Do not be limited by your craft background, in serving your paymasters
Copyright 2004-8 Gilb, may be used citing source
“Values for Value”
http://www.gilb.com/tiki-download_file.php?fileId=448
Agile Record 2010, www.agilerecord.com, October 2010, Issue 4
Notes: Created Thursday, November 25, 2004 during XP conf London lecture by Tom@Gilb.com
http://www.gilb.com/tiki-download_file.php?fileId=456
What are the Dangers of Current Agile Practices, and How Can We Fix Them?
Values for Value
by Tom Gilb & Lindsey Brodie
Some Alternative Ideas On Agile Values For Delivering Stakeholder Value Principles and Values – Agility is the Tool, Not the Master.
Part 2 “Values for Value”
http://www.gilb.com/tiki-download_file.php?fileId=448
Agile Record 2010, www.agilerecord.com, October 2010, Issue 4

## Slide 72
Ecstatic Stakeholder!
Notes: http://www.centerforvibrationalhealing.info/images/ecstatic-woman.jpg

## Slide 73: That’s All Folks!
Discussion?
  I am here all Conference and incl My Friday ‘Evo’ Seminar
  And love to talk with you!
Remarks? Questions?
  Email me if you like
For free digital copy of this book, and 4 of my Agile papers, and the Evo book
Email me subject “Book”
Tom@Gilb.com
If you want to agree a meeting, email me
or text +47 92066705
This talk is NOW at Gilb.com/Downloads (Slides)

## Slide 74: Agile Credibility
Agile ‘Grandfather’ (Tom)
  Practicing ‘Agile’ IT Projects since 1960
  Preaching Agile since 1970’s (CW UK)
  Acknowledged Pioneer by Agile Gurus and Research
    Beck, Sutherland, Highsmith, Cohn, Larman etc.
    Ask me for details on this! I am too shy to show it here!
Agile Practice
  IT: for decades (Kai and Tom)
  Organisations: for Decades (Citigroup, Intel, HP, Boeing)
Books:
  Principles of Software Engineering Management (1988) the book Beck and others refer to
  Competitive Engineering (2005)
  Evo: (Kai, evolving, 55 iterations)
Notes: Agile References:
"Tom Gilb invented Evo, arguably the first Agile process. He and his son Kai have been working with me in Norway to align what they are doing with Scrum.
Kai has some excellent case studies where he has acted as Product Owner. He has done some of the most innovative things I have seen in the Scrum community."
Jeff Sutherland, co-inventor of Scrum, 5Feb 2010 in Scrum Alliance Email.
“Tom Gilb's Planguage referenced and praised at #scrumgathering by Jeff Sutherland. I highly agree" Mike Cohn, Tweet, Oct 19 2009
“I’ve always considered Tom to have been the original agilist. In 1989, he wrote about short iterations (each should be no more than 2% of the total project schedule). This was long before the rest of us had it figured out." Mike Cohn http://blog.mountaingoatsoftware.com/?p=77
Comment of Kent Beck on Tom Gilb’s book , “Principles of Software Engineering Management”: “ A strong case for evolutionary delivery – small releases, constant refactoring, intense dialog with the customer”. (Beck, page 173).
In a mail to Tom, Kent wrote: “I'm glad you and I have some alignment of ideas. I stole enough of yours that I'd be disappointed if we didn't :-), Kent” (2003)
"But if you really want to take a step up, you should read Tom Gilb. The ideas expressed in Principles of Software Engineering Management aren’t quite fully baked into the ADD-sized nuggets that today’s developers might be used to, but make no mistake, Gilb’s thinking on requirements definition, reliability, design generation, code inspection, and project metrics are beyond most current practice." Corey Ladas http://leansoftwareengineering.com/2007/12/20/tom-gilbs-evolutionary-delivery-a-great-improvement-over-its-successors/
Jim Highsmith (an Agile Manifesto signatory) commented: “Two individuals in particular pioneered the evolution of iterative development approached in the 1980’s – Barry Boehm with his Spiral Model and Tom Gilb with his Evo model. I drew on Boehm’s and Gilb’s ideas for early inspiration in developing Adaptive Software Development. …. Gilb has long advocated this more explicit (quantitative) valuation in order to capture the early value and increase ROI” (Cutter It Journal: The Journal of Information Technology Management, July 2004page 4, July 2004).
Ward Cunningham wrote April 2005: “Tom -- Thanks for sharing your work. I hope you find value in ours. I'm also glad that the agile community is paying attention to your work. We know (now) that you were out there ahead of most of us. Best regards. – Ward”, http://c2.com
Robert C. Martin (Agile Manifesto initial signatory, aka Uncle Bob): "Tom and I talked of many things, and I found myself learning a great deal from him. The item that sticks most prominently in my mind is the definition of progress.", "Tom has invented a planning formalism that he calls Planguage that captures this idea of customer need. I think I'm going to spend some serious time investigating this. " from http://www.butunclebob.com/ArticleS.UncleBob.TomGilbVisit
'1985: perhaps the first explicitly named, incremental alternative to the “waterfall” approach is Tom Gilb’s Evolutionary Delivery Model, nicknamed “Evo” '
http://guide.agilealliance.org/timeline.html
Gilb T. (1985). "Evolutionary Delivery versus the "waterfall model" " ACM SIGSOFT, http://dl.acm.org/citation.cfm?id=1012490
Mary Poppendieck, 2012
In 1988, Tom Gilb wrote the book Principles of Software Engineering Management, which is now in its 20th printing. One of the earliest advocates of evolutionary development, he has recently reiterated the elements of good software engineering in an article in Agile Record[2], from which I quote liberally
http://poppendieck.blogspot.com/2010/12/product-owner-problem.html
Agile History…
Historical Roots of Agile Methods:
Where did “Agile Thinking” Come from?
Noura Abbas, Andrew M Gravell, Gary B Wills
School of Electronics and Computer Science, University of Southampton
Southampton, SO17 1BJ, United Kingdom
( Oct 10 2008)
http://eprints.ecs.soton.ac.uk/16606/1/xp2008camera_ready.pdf
"Agile ideas appeared in old development processes as well. In 1985, Tom Gilb wrote “Evolutionary Delivery versus the ‘Waterfall model’”. In this paper Gilb introduce the EVO method as an alternative of the waterfall which he considered as “unrealistic and dangerous to the primary objectives of any software project”. Gilb based EVO on three simple principles [17]:
• Deliver something to the real end-user
• Measure the added-value to the user in all critical dimensions
• Adjust both design and objectives based on observed realities "

## Slide 75: OK I am not that shy! (the most influential!)
Agile References:
"Tom Gilb invented Evo, arguably the first Agile process. He and his son Kai have been working with me in Norway to align what they are doing with Scrum.
Kai has some excellent case studies where he has acted as Product Owner. He has done some of the most innovative things I have seen in the Scrum community."
Jeff Sutherland, co-inventor of Scrum, 5Feb 2010 in Scrum Alliance Email.
“Tom Gilb's Planguage referenced and praised at #scrumgathering by Jeff Sutherland. I highly agree" Mike Cohn, Tweet, Oct 19 2009
“I’ve always considered Tom to have been the original agilist. In 1989, he wrote about short iterations (each should be no more than 2% of the total project schedule). This was long before the rest of us had it figured out." Mike Cohn http://blog.mountaingoatsoftware.com/?p=77
Comment of Kent Beck on Tom Gilb’s book , “Principles of Software Engineering Management”: “ A strong case for evolutionary delivery – small releases, constant refactoring, intense dialog with the customer”. (Beck, page 173).
In a mail to Tom, Kent wrote: “I'm glad you and I have some alignment of ideas. I stole enough of yours that I'd be disappointed if we didn't :-), Kent” (2003)
Jim Highsmith (an Agile Manifesto signatory) commented: “Two individuals in particular pioneered the evolution of iterative development approached in the 1980’s – Barry Boehm with his Spiral Model and Tom Gilb with his Evo model. I drew on Boehm’s and Gilb’s ideas for early inspiration in developing Adaptive Software Development. …. Gilb has long advocated this more explicit (quantitative) valuation in order to capture the early value and increase ROI” (Cutter It Journal: The Journal of Information Technology Management, July 2004page 4, July 2004).
Notes: Agile References:
"Tom Gilb invented Evo, arguably the first Agile process. He and his son Kai have been working with me in Norway to align what they are doing with Scrum.
Kai has some excellent case studies where he has acted as Product Owner. He has done some of the most innovative things I have seen in the Scrum community."
Jeff Sutherland, co-inventor of Scrum, 5Feb 2010 in Scrum Alliance Email.
“Tom Gilb's Planguage referenced and praised at #scrumgathering by Jeff Sutherland. I highly agree" Mike Cohn, Tweet, Oct 19 2009
“I’ve always considered Tom to have been the original agilist. In 1989, he wrote about short iterations (each should be no more than 2% of the total project schedule). This was long before the rest of us had it figured out." Mike Cohn http://blog.mountaingoatsoftware.com/?p=77
Comment of Kent Beck on Tom Gilb’s book , “Principles of Software Engineering Management”: “ A strong case for evolutionary delivery – small releases, constant refactoring, intense dialog with the customer”. (Beck, page 173).
In a mail to Tom, Kent wrote: “I'm glad you and I have some alignment of ideas. I stole enough of yours that I'd be disappointed if we didn't :-), Kent” (2003)
"But if you really want to take a step up, you should read Tom Gilb. The ideas expressed in Principles of Software Engineering Management aren’t quite fully baked into the ADD-sized nuggets that today’s developers might be used to, but make no mistake, Gilb’s thinking on requirements definition, reliability, design generation, code inspection, and project metrics are beyond most current practice." Corey Ladas http://leansoftwareengineering.com/2007/12/20/tom-gilbs-evolutionary-delivery-a-great-improvement-over-its-successors/
Jim Highsmith (an Agile Manifesto signatory) commented: “Two individuals in particular pioneered the evolution of iterative development approached in the 1980’s – Barry Boehm with his Spiral Model and Tom Gilb with his Evo model. I drew on Boehm’s and Gilb’s ideas for early inspiration in developing Adaptive Software Development. …. Gilb has long advocated this more explicit (quantitative) valuation in order to capture the early value and increase ROI” (Cutter It Journal: The Journal of Information Technology Management, July 2004page 4, July 2004).
Ward Cunningham wrote April 2005: “Tom -- Thanks for sharing your work. I hope you find value in ours. I'm also glad that the agile community is paying attention to your work. We know (now) that you were out there ahead of most of us. Best regards. – Ward”, http://c2.com
Robert C. Martin (Agile Manifesto initial signatory, aka Uncle Bob): "Tom and I talked of many things, and I found myself learning a great deal from him. The item that sticks most prominently in my mind is the definition of progress.", "Tom has invented a planning formalism that he calls Planguage that captures this idea of customer need. I think I'm going to spend some serious time investigating this. " from http://www.butunclebob.com/ArticleS.UncleBob.TomGilbVisit
'1985: perhaps the first explicitly named, incremental alternative to the “waterfall” approach is Tom Gilb’s Evolutionary Delivery Model, nicknamed “Evo” '
http://guide.agilealliance.org/timeline.html
Gilb T. (1985). "Evolutionary Delivery versus the "waterfall model" " ACM SIGSOFT, http://dl.acm.org/citation.cfm?id=1012490
Mary Poppendieck, 2012
In 1988, Tom Gilb wrote the book Principles of Software Engineering Management, which is now in its 20th printing. One of the earliest advocates of evolutionary development, he has recently reiterated the elements of good software engineering in an article in Agile Record[2], from which I quote liberally
http://poppendieck.blogspot.com/2010/12/product-owner-problem.html
Agile History…
Historical Roots of Agile Methods:
Where did “Agile Thinking” Come from?
Noura Abbas, Andrew M Gravell, Gary B Wills
School of Electronics and Computer Science, University of Southampton
Southampton, SO17 1BJ, United Kingdom
( Oct 10 2008)
http://eprints.ecs.soton.ac.uk/16606/1/xp2008camera_ready.pdf
"Agile ideas appeared in old development processes as well. In 1985, Tom Gilb wrote “Evolutionary Delivery versus the ‘Waterfall model’”. In this paper Gilb introduce the EVO method as an alternative of the waterfall which he considered as “unrealistic and dangerous to the primary objectives of any software project”. Gilb based EVO on three simple principles [17]:
• Deliver something to the real end-user
• Measure the added-value to the user in all critical dimensions
• Adjust both design and objectives based on observed realities "

## Slide 76: TWELVE TOUGH QUESTIONS
1. Why isn't the improvement quantified?
2. What is degree of the risk or uncertainty and why?
3. Are you sure? If not, why not?
4. Where did you get that from? How can I check it out?
5. How does your idea affect my goals, measurably?
6. Did we forget anything critical to survival?
7. How do you know it works that way? Did it before?
8. Have we got a complete solution? Are all objectives satisfied?
9. Are we planning to do the 'profitable things' first?
10. Who is responsible for failure or success?
11. How can we be sure the plan is working, during the project, early?
12. Is it ‘no cure, no pay’ in a contract? Why not?
There is a detailed paper on these questions at Gilb.com
http://www.gilb.com/tiki-download_file.php?fileId=24